## Sheet1
| Action | Responsible | Due Date |  | Days from Launch
Phase 1 | Solo Scheduling | Email Team
Step 2 | Copy points, Design considerations in Approved Brief due from business partner. | Business Partner/CM | 2017-06-19 | Monday | -42
Step 3 | CM send draft schedule to YesMail (Diana Strandberg & Lauren Kelp) and Epsilon (IC-Marriott@epsilon.com) for sign off | CM/Yesmail/Epsilon | 2017-06-21 | Wednesday | -40
Phase 2 | Design Development & Targeting | Design Team
Step 4 | CM kicks off design with YesMail | CM/Yesmail | 2017-06-23 | Friday | -38
Step 5 | Yesmail provides Project Summary Brief to CM for review and feedback | Yesmail/CM | 2017-06-26 | Monday | -37
Step 6 | Yesmail provides Round 1 Design and Copy | Yesmail | 2017-06-30 | Friday | -33
Step 7 | CM compiles internal feedback on Round 1 Copy & Design and sends to Yesmail via Message Tracker | CM | 2017-07-03 | Monday | -32
Step 8 | Yesmail provides Round 2 Design & Copy that CM sends to business partner for review | Yesmail | 2017-07-06 | Thursday | -30
Step 9 | CM compiles all feedback on Round 2 Design & Copy and sends to Yesmail via Message Tracker | CM | 2017-07-10 | Monday | -28
Step 10 | CM send Yesmail Link Matrix for coding | CM | 2017-07-10 | Monday | -28
Step 11 | Yesmail provides Round 3 Design & Copy that CM sends to business partner, legal and proof reading for approval | Yesmail/CM | 2017-07-12 | Wednesday | -26
Step 12 | CM compiles approval/feedback from stakeholders and works with Yesmail to finalize assets | CM | 2017-07-14 | Friday | -24
Step 13 | Final coded assets to Epsilon | Yesmail | 2017-07-18 | Tuesday | -22
Step 14 | CM submits campaign targeting request through UNICA | CM | 2017-07-25 | Tuesday | -17
Phase 3 | Email Set-up and Targeting | Campaign Build Team
Step 15 | CM sends both a JT and test list to Epsilon and holds asset review call with Yesmail, Epsilon (if necessary) | CM | 2017-07-18 | Tuesday | -22
Step 16 | Epsilon sends Round 1 tests to CM and Yesmail | CM/Yesmail/Epsilon | 2017-07-25 | Tuesday | -17
Step 17 | CM distributes to Email Campaign Review Essentials-ROUND1 list (includes key stakeholders, Email team, Legal, and Proofreading). | CM | 2017-07-25 | Tuesday | -17
Step 18 | CM & Yesmail contact hold Litmus review call | CM/Yesmail | 2017-07-26 | Wednesday | -16
Step 19 | CM responsible for compiling feedback from various teams and submits a PDF with edits. CM is responsible for QA of links & tracking codes. Yesmail for creative rendering. Epsilon for Link Rendering & scripting | CM | 2017-07-31 | Monday | -13
Step 20 | CM & Yesmail receive next round of tests from Epsilon. CM is responsible for QA of links & tracking codes. Yesmail for creative rendering. Epsilon for Link Rendering | Epsilon | 2017-08-02 | Wednesday | -11
Step 21 | CM distributes final tests to ROUND 2 test list (anyone that submitted changes from Round 1 test review + business owners) for final review | CM | 2017-08-11 | Friday | -4
Step 22 | Epsilon receives Mailing File | Marketing Systems | 2017-08-11 | Friday | -4
Step 23 | CM captures written sign off from business owner for deployment and provides final test + deployment details (date, time) | CM | 2017-08-15 | Tuesday | -2
Step 24 | CM sends seed list to Epsilon | CM | 2017-08-15 | Tuesday | -2
Step 25 | CM reviews live tests, seed lives, approves and schedules launch. CM sends out Email Campaign Launch Notification Email to key stakeholders | CM | 2017-08-16 | Wednesday | -1
Step 26 | CM approves scheduling notification | CM | 2017-08-16 | Wednesday | -1
EMAIL LAUNCH DATE |  |  | 2017-08-17 | Thursday | 0
Formulas:
Due Date = WORKDAY(D33,[Days from Launch],Sheet2!$B2:B13)

## Sheet2
Holidays
Thanksgiving | 2016-11-24
Thanksgiving | 2016-11-25
Christtmas | 2016-12-25
New Year | 2017-01-02
MLK | 2017-01-16
Presidents | 2017-02-20
Memorial | 2017-05-29
Independence | 2017-07-04
Labor | 2017-09-04
Thanksgiving | 2017-11-23
Thanksgiving | 2017-11-24
Christtmas | 2017-12-25
Weekday
1 | Sunday
2 | Monday
3 | Tuesday
4 | Wednesday
5 | Thursday
6 | Friday
7 | Saturday