## 2019 Master
| Campaign | Campaign Manager | Business Partners | Translation | SiteCore | Wylei | Internal Stage | Status/Notes | Unica Ticket Number | Unica Submission Due | Unica Final Data Requirements Due | Creative Kick-off | Message Briefing Doc | Design Round 1 | DR 1 Feedback | Design Round 2 | DR 2 Feedback & Link Matrix | Final Design | Approval | Coding | CrS & Functional QA | EN Hand-off Epsilon/EN Assets Posted to Portal | Link Matrices Due | Hand-off | Test Launch | Feedback to MR | Launch
[12 empty] | 1 day | 1 day | 1 day/1pmEST | 2 days | 2 days | 2 days | 1 day | 1 day | 1.5 days | .5 days | 0 days | 1 day | 1 day | 1 day | 2 days
Template
MAR-0761, password: bonvoyage | OBOP Template EN | Diana |  |  |  |  | Epsilon Test | With Epsilon for integration into Harmony. | N/A | N/A | N/A | 2018-09-24 |  | 2018-10-18 | 2018-10-22 | 2018-11-02 | 2018-11-02 | 2018-11-06 | 2018-11-08 | 2019-11-09 | 2018-11-06 |  |  | 2018-11-21
MAR-0761 | OBOP Template In-Language | Diana |  | CN, ES, FR, DE, JP, BR, RU, IT, BR EN, FR CAN |  |  | Epsilon Test | With Epsilon for integration into Harmony. | N/A | N/A | N/A | [10 empty] | 2018-11-26 | 2018-11-28 | w/o 12/17
MAR-0761 | OBOP Template SiteCore | Diana |  |  |  |  | Planning | On hold. | N/A | N/A | N/A
Autos
MAR-0593 | Marriott Append Project (Internal) | Diana |  | N/A |  | n/a | Planning | On hold. | TBD | TBD | TBD |  |  | 2018-02-14 | 2018-02-15 | 2018-02-15 | 2018-02-15 | 2018-02-15 | 2018-02-16 | 2018-02-15 | 2018-02-16 |  |  | 2018-02-21 | TBD
MAR-0752 | OBOP Migration Retrofit | Mimi/Brittany |  |  |  |  | Web Prod | Batch 1 - awaiting for the footer to do a thorough review - Batch 2/3 in build with Epsilon - prioritizing Combine Accounts - mailing file name confirmation | N/A | N/A | N/A
2019-01-01
| Targted Booking Solo | Meghan |  |  |  |  | z-Not Started | Confirming if happening |  | 2018-12-03 | 2018-12-11 | 2018-11-26 | 2018-11-27 | 2018-11-30 | 2018-12-03 | 2018-12-05 | 2018-12-07 | 2018-12-11 | 2018-12-13 | 2018-12-14 | 2018-12-17 |  |  | 2018-12-18 | 2018-12-20 | 2018-12-26 | 2019-01-04
MAR-0736 | eNews January | Lisa |  |  |  |  | Completed | Launching 1/23. |  | 2018-12-20 | 2018-12-28 | 2018-11-19 | 2018-11-20 | 2018-11-29 | 2018-11-30 | 2018-12-04 | 2018-12-06 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 |  |  | 2018-12-14 | 2018-12-26 | 2018-12-28 | 2019-01-23
MAR-0809 | MRCC Acquisition January Resend | Kaitlin |  |  |  |  | Completed | Launched 1/18 |  | 2018-12-11 | 2018-12-19 | 2018-12-04 | 2018-12-05 | 2018-12-10 | 2018-12-11 | 2018-12-13 | 2018-12-17 | 2018-12-19 | 2018-12-21 | 2018-12-26 | 2018-12-27 |  |  | 2018-12-28 | 2019-01-08 | 2019-01-09 | 2019-01-18
MAR-0771 | Destinations January | Kaitlin |  |  |  |  | Epsilon Retest | Received Seeds/Lives 1/22. Need final approval from Sabina & Orsi. | TBD | 2018-12-24 | 2019-01-03 | 2018-12-17 | n/a | 2018-12-21 | 2018-12-27 | 2019-01-01 | 2019-01-03 | 2019-01-04 | 2019-01-07 | 2019-01-08 | 2019-01-10 |  |  | 2019-01-11 | 2019-01-15 | 2019-01-17 | 2019-01-25
MAR-0751 | Moments January | Kaitlin |  |  |  |  | Epsilon Retest | Creative approved by BP. Wylei site-scrape IDs due 1/23. Counts sent to Eps 1/23. Expecting seeds and lives 1/24. |  | 2018-12-27 | 2019-01-07 | 2018-12-18 | 2018-12-19 | 2018-12-21 | 2018-12-27 | 2019-01-01 | 2019-01-03 | 2019-01-07 | 2019-01-09 | 2019-01-10 | 2019-01-11 |  |  | 2019-01-14 | 2019-01-16 | 2019-01-18 | 2019-01-28
MAR-0772 | Hotel Specials January | Meghan |  |  |  | nav bar | Epsilon Test | R1 test feedback due to Epsilon 1/23. Litmus completed 1/17 - No issues. |  | 2018-12-28 | 2019-01-09 | 2018-12-20 | 2018-12-21 | 2018-12-28 | 2019-01-03 | 2019-01-04 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-09 | 2019-01-09 |  |  | 2019-01-10 | 2019-01-22 | 2019-01-24 | 2019-01-31
2019-02-01
MAR-0768 | COBRAND: Chase RAF | Kaitlin |  |  |  |  | Epsilon Retest | Creative approved by MR & bank. Waiting on data file 1/25. | TBD | 2019-01-01 | 2019-01-09 | 2018-12-20 | 2018-12-21 | 2018-12-28 | 2019-01-01 | 2019-01-03 | 2019-01-07 | 2019-01-09 | 2019-01-11 | 2019-01-14 | 2019-01-15 |  |  | 2019-01-16 | 2019-01-18 | 2019-01-22 | 2019-02-01
MAR-0817 | Mobile App Solo | Mimi |  |  |  |  | Design | Expecting PSD file today, 1/23 |  | 2019-01-03 | 2019-01-11 | 2018-12-25 | 2018-12-26 | 2019-01-02 | 2019-01-03 | 2019-01-07 | 2019-01-09 | 2019-01-11 | 2019-01-15 | 2019-01-16 | 2019-01-17 |  |  | 2019-01-18 | 2019-01-23 | 2019-01-25 | 2019-02-04
MAR-0818 | COBRAND: CHASE ACQ - 75K PTS Re-mail | Kaitlin |  |  |  |  | Epsilon Test | Creative approved by bank. Waiting on data file. |  | 2019-01-03 | 2019-01-11 | 2018-12-14 | n/a | 2018-12-19 | 2018-12-21 | 2018-12-24 | 2018-12-25 | 2018-12-27 | 2019-01-02 | 2019-01-03 | 2019-01-04 |  |  | 2019-01-07 | 2019-01-17 | 2019-01-29 | 2019-02-05
Formulas:
Unica Submission Due = WORKDAY([Launch],-21,Holidays!$A:$A)
Unica Final Data Requirements Due = WORKDAY([Launch],-15,Holidays!$A:$A)

## RCR
RC BAU
Campaign | Notes | Unica Ticket Number | Unica Submission Due (21 days from launch) | Unica Final Data Requirements Due (15 days from launch) | Creative Kick-off | Design Round 1 comps due | Design Round 1 Call | Design Review 1 Feedback | Design Round 2 | DR 2 Feedback | Final Design | Approval | Coding | QA | Hand-off to Epsilon | Test Launch | Feedback to Epsilon | Launch | Campaign | Project # | Status | Designer | Content Outline | Billing
October | [18 empty] | October
October eNews | Deployed |  |  |  | 2018-08-21 | 2018-09-06 | 2018-09-07 | 2018-09-12 | 2018-09-14 | 2018-09-18 | 2018-09-24 | 2018-09-25 | 2018-09-26 | 2018-09-27 | 2018-10-05 | 2018-10-09 | 2018-10-15 | 2018-10-17 | October eNews |  | Deployed
Dorado Beach Rush Solo | Deployed |  |  |  | 2018-09-25 | 2018-09-28 | 2018-10-01 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 10/4 or 10/5 | 2018-10-05 | 2018-10-09 | 2018-10-15 | 2018-10-15 | Dorado Beach Rush Solo |  | Deployed |  |  | Bill Incremental
October eNews Lite | Deployed |  |  |  | 2018-09-20 | 2018-10-01 | 2018-10-03 | 2018-10-05 | 2018-10-09 | 2018-10-11 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-15 | 2018-10-17 | 2018-10-23 | 2018-10-25 | 2018-10-29 | October eNews Lite |  | Deployed
Choice Of Reminder | Approved |  |  |  | 2018-09-20: 2018-09-17; 2018-10-01: 2018-09-19; 2018-10-12: 2018-09-25; 2018-10-17: TBD; 2018-10-23: TBD; 2018-10-25: TBD; 2018-10-29: TBD | Choice Of Reminder |  | Complete |  |  | Bill Incremental
Choice Of Default Notification | Approved |  |  |  | 2018-09-20: 2018-09-17; 2018-10-01: 2018-09-19; 2018-10-12: 2018-09-25; 2018-10-17: TBD; 2018-10-23: TBD; 2018-10-25: TBD; 2018-10-29: TBD | Choice Of Default Notification |  | Complete |  |  | Bill Incremental
November | [18 empty] | November
Yacht Collection Solo | Deployed |  | Francesca CM |  | 2018-10-03 | 2018-10-09 | 2018-10-10 | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-26 |  |  | 2018-10-22 | 2018-10-24 | 2018-10-31 | 2018-11-01 | 2018-11-07 | Yacht Collection Solo | TRC 0006 | Deployed |  |  | Bill Incremental
November eNews | Deployed | 20181114_RC_ENEWS | Complete | Complete | 2018-10-02 | 2018-10-10 | 2018-10-11 | 2018-10-15 | 2018-10-17 | 2018-10-19 | 2018-10-22 | 2018-10-30 | 2018-10-31 | 2018-10-31 | 2018-11-01 | 2018-11-07 | 2018-11-09 | 2018-11-14 | November eNews | TRC 0005 | Deployed
November RCR Cardholder eNews | Deployed | 20181126_RCR_CARDHOLDER_NEWSLETTER | Complete | Complete | 2018-11-02 | 2018-11-06 | NA | 2018-11-07 | 2018-11-08 | NA | 2018-11-09 | 2018-11-14 | 2018-11-15 | 2018-11-15 | 2018-11-16 | 2018-11-20 | 2018-11-26 | 2018-11-28 | November RCR Cardholder eNews | TRC 0007 | Deployed | Christina
November Reserve Solo | Deployed |  | Francesca CM |  | 2018-10-29 | 2018-10-31 | 2018-10-31 | 2018-10-31 | 2018-11-01 | 2018-11-01 | 2018-11-02 | 2018-11-02 | 2018-11-05 | 2018-11-05 | 2006-11-05 | 2018-11-07 | 2018-11-08 | 2018-11-12 | November Reserve Solo | TRC 0009 | Deployed |  |  | Bill Incremental
December | [18 empty] | December
December eNews | Deployed | 20181212_RC_ENEWS | Complete | Complete | 2018-10-26 |  | 2018-11-06 | 2018-11-07 | 2018-11-14 | 2018-11-16 | 2018-11-19 | 2018-11-21 | 2018-11-26 | 2018-11-26 | 2018-11-27 | 2018-12-03 | 12/618 | 2018-12-12 | December eNews | TRC 0008 | Deployed | Sterling | https://docs.google.com/document/d/1g2JtHEb_Bo2UDsGGnZ_VRAbChbPB8pChHRZJoes_3JA/edit
December eNews Lite | Deployed | 20181219_RC_ENEWSLITE | Complete | Complete | 2018-11-02 |  | 2018-11-14 | 2018-11-16 | 2018-11-20 | 2018-11-26 | 2018-11-28 | 2018-11-30 | 2018-12-03 | 2018-12-03 | 2018-12-04 | 2018-12-07 | 2018-12-17 | 2018-12-21 | December eNews Lite | TRC 0010 | Deployed | Sterling | https://docs.google.com/document/d/1YE9RZN8uKgLaEmqM8mNGjcpp155A46YMpf4z0gW9Yh8/edit
January | [18 empty] | January
January eNews | Awaiting final lives and JT with counts from Epsilon, the launch notification to be shared this afternoon | 2019124_RC_ENEWS | 2018-12-21 | 2019-01-03 | 2018-11-29 | 2018-12-07 | 2018-12-11 | 2018-12-14 | 2018-12-18 | 2018-12-20 | 1/3-1/4 | 1/7-1/8 | 1/8-1/9 | 1/8-1/9 | 2019-01-09 | 2019-01-17 | 2019-01-18 | 2019-01-24 | January eNews (TBD) | TRC 0011 | With Epsilon | Sterling
February | [18 empty] | January
Yacht Collection Solo | Campaign subimitted 1/22, deployment moved to 1/30. YM team will handle Litmus review and any necessary code fixes |  | Francesca CM |  | 2019-01-18 | 2019-01-21 | NA | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-25 | NA | NA | 2019-01-28 | 2019-01-31 | 2019-02-04 | 2019-02-07 | Yacht Collection Solo | TRC 0012 |  |  |  | Bill Incremental

## TeamAvailability
| Marriott/Yesmail | Dates out of Office | Coverage
President's Day | Marriott & Yesmail | Mon 2/17 | n/a
Afton McMann | Yesmail | Tue 2/18 - Fri 2/21 | Michael Parapetti
Lisa Cannon | Marriott | Thu 2/19 - Fri 2/21 | Clark Cummings
Kerry Mealia | Marriott | Fri 2/21
Alicia Cruz | Yesmail | Mon 2/24 - Fri 2/28 | Edan Lisk
Edan Lisk | Yesmail | Wed 2/26 - limited availability
Jaya Nessiar | Marriott | Wed 2/26 - Thu 2/27
Edan Lisk | Yesmail | Fri 2/28
Kerry Mealia | Marriot | Fri 3/21
Afton McMann | Yesmail | Fri 4/4 | Mike Parapetti
Lisa Cannon | Marriott | Fri 4/4
Marriott Team | Marriott | Mon 4/7 - Wed 4/9 | Team Meeting
Edan Lisk | Yesmail | Mon 4/14
Edan Lisk | Yesmail | Fri 4/18 | Alicia Cruz
Kerry Mealia | Marriott | Mon 4/21
Amy Anspach | Marriott | Mon 4/21 - Wed 4/23
Courtney Knowles | Marriott | Mon 4/21 - Fri 4/25
Amy Anspach | Marriott | Fri 5/16 & Mon 5/19
Jaya Nessiar | Marriott | Tue 5/20 & Wed 5/21
Clark Cummings | Marriott | Thu 5/22 - Tues 5/27
Edan Lisk | Yesmail | Fri 5/23
Jaya Nessiar | Marriott | Tues 6/3 - Wed 6/4
Mike Parapetti | Yesmail | Wed 6/4
Edan Lisk | Yesmail | Thu 6/5 - Fri 6/6
Afton McMann | Yesmail | Tue 6/10 - Wed 6/11
Courtney Knowles | Marriott | Fri 6/13 half-day
Amy Anspach | Marriott | Mon 6/16 - Fri 6/20
Jaya Nessiar | Marriott | Tues 6/17 - Fri 6/20
Courtney Knowles | Marriott | Mon 6/23 - Tues 6/24
Jaya Nessiar | Marriott | Wed 6/25 - Fri 6/27
Yesmail Team | Yesmail | Thur 7/3 | n/a - holiday
Edan Lisk | Yesmail | 1/2 day - Fri 7/25
Kerry Mealia | Marriott | Fri 7/25
Mike Parapetti | Yesmail | 8/28-9/2
Megan Holland | Yesmail | 2014-08-29
Lisa Cannon | Marriott | 9/8 - 9/9
Kerry Mealia | Marriott | 9/10-9/12 & 9/15 AM
Kerry Mealia | Marriott | 2014-09-19
Amy Anspach | Marriott | 9/25 - 10/1
Afton McMann | Yesmail | 10/2 - 10/3 | Mike Parapetti
Edan Lisk | Yesmail | 10/9 - 10/10 | Amy McNeil
Kerry Mealia | Marriott | 10/22 - 11/4 AM
Courtney Knowles | Marriott | 9/12 & 9/15
Courtney Knowles | Marriott | 10/10-10/13
Lisa Cannon | Marriott | 11/4 - 11/11 | Clark
Clark Cummings | Marriott | 11/7 - 11/10
Courtney Knowles | Marriott | Mon 11/10
Afton McCann | Yesmail | Fri 10/24
Brandon | Yesmail | Fri 10/24
Megan Oster | Yesmail | Fri 10/24
Brandon | Yesmail | Mon 11/14 & Fri 11/17 | Karrie/Brenna
Afton | Yesmail | Mon 11/10
Megan Holland | Yesmail | 11/11-11/14 | Cynthia
Clark Cummings | Marriott | Fri 11/21 PM
Clark Cummings | Marriott | Mon 11/24 - Wed 11/26
Ted Kim | Yesmail | Wed 11/26
Yesmail & Marriott Teams | Yesmail | Thu 11/27 - Fri 11/28 | Holiday
Clark Cummings | Marriott | Fri 12/5 - Wed 12/10
Megan Holland | Yesmail | Thurs 12/4/2014 | Cynthia
Megan Holland | Yesmail | Mon 12/8- Wed 12/10 | Cynthia
Lisa Cannon | Marriott | Mon 12/8 - Fri 12/12 | Clark
Mike Parapetti | Yesmail | 3/12-3/13
Diego Saenz | Yesmail | 3/13-3/20
Clark, Marc, Sarah | Marriott | 4/22 - 4/24
Entire MR Email Team | Marriott | 4/27 - 4/29
Kerry Greene | Marriott | 2015-05-01
Megan Holland | Yesmail | 2015-04-21 | Ravi Rao
Megan Holland | Yesmail | 4/27-5/1 | Ravi Rao
August
Lisa Kackos | Yesmail | 8/17 - 8/29 | Diana Strandberg
Ravi Rao | Yesmail | 8/24-8/26 | Megan Holland
Jen Tabbal | Yesmail | 8/24 - 8/28 | Edan/Diana/Shannon
Ted Kim | Yesmail | 8/24 - 8/27 | Bryan Finke
Jess Moss | Yesmail | 8/25-8/26
Diana Strandberg | Yesmail | 9/1-9/8 | Lisa Kackos
May
Jaya Nessiar | Marriott | 5/31, 6/1
Marriott out of pocket- all day events | Marriott | 2016-05-25
Shannon Morgan | Yesmail | 5/20 & 5/23 | Available by phone
Clark Cummings | Marriott | 5/26,5/27,5/31
Lisa Kackos | Yesmail | 2016-05-27 | Diana
Jess Moss | Yesmail | 5/23-5/27 | Shannon/Jen (I will be reachable too)
Kerry Greene | Marriott | 2016-05-27
Mike Parapetti | Yesmail | 5/26- 5/27
Nick Bay | Yesmail | 2016-05-31
Dina Touchon | Yesmail | 2017-01-16 | Neil, Ravi
May
Brandon | Yesmail | 2017-05-19
Meghan Monahan | Yesmail | 5/24 - 5/26 | Diana, Rachel
Afton McCann | Yesmail | 2017-05-30 | Sterling, Christina, Danielle
July
Danielle McNamara | Yesmail | 7/5 - 7/11 | Afton, Sterling
Lisa Cannon | Marriott | 7/7 - 7/14
Diana Strandberg | Yesmail | 7/13, 7/14, 7/17 | Meghan, Rachel
Brandon Scheiner | Yesmail | 7/14, 7/17 | Bill
Leigh Strickland | Marriott | 2017-07-21
Dina Touchon | Yesmail | 7/21 - 8/1 | Ravi
Neil Arsenty | Yesmail | 7/21, 7/31 | Ravi
Clark Cummings | Marriott | 2017-07-24
Jen Tabbal | Yesmail | 7/24-7/28
August
Meghan Monahan | Yesmail | 2017-08-04 | Diana, Rachel
Matt Caldwell | Yesmail | 8/6 - 8/21
Jen Tabbal | Yesmail | 8/7-8/11 (Not on PTO but not 100% available)
Clark Cummings | Marriott | 2017-08-07
Lisa Cannon | Marriott | 8/9 - 8/14
Ravi Rao | Yesmail | 8/7 - 8/11 | Neil, Dina
Meghan Monahan | Yesmail | 8/10 - 8/14 | Diana, Rachel
Afton McCann | Yesmail | 8/9 - 8/15 | Sterling, Christina, Danielle
Sterling Crain | Yesmail | 8/14 - 8/18 | Afton, Danielle
Diana Strandberg | Yesmail | 2017-08-18
Neil Arsenty | Yesmail | 8/21 (half-day), 8/22 - 8/23 | Dina, Ravi
Ravi Rao | Yesmail | 2017-08-25 | Neil, Dina
Kerry Greene | Marriott | 8/31-9/5
Diana Strandberg | Yesmail | 8/31-9/1 | Meghan, Rachel
Dina Touchon | Yesmail | 8/27 - 8/31 | Neil, Ravi
September
Kaitlin Seger | Yesmail | 9/7-9/10 | Meghan, Mimi, Maureen
Jess Moss | Yesmail | 9/11-9/15 | Jen
Brandon Scheiner | Yesmail | 9/15, 9/29 | Bill, Jun
Heather Bien | Yesmail | 9/19-9/25
Leigh Strickland | Marriott | 2017-09-20
Neil Arsenty | Yesmail | 9/28-9/29 | Dina, Ravi
Rachel Skolnick | Yesmail | 9/28-9/29 | Meghan, Diana
October
Clark Cummings | Marriott | 2017-10-16
Rachel Skolnick | Yesmail | 10/17 - 10/18 | Diana, Meghan
Meghan Monahan | Yesmail | 10/19 - 10/27 | Diana, Rachel
Brandon Scheiner | Yesmail | 10/30, 10/31 | Bill, Jun
November
Kerry Greene | Marriott | 11/2-3
Afton McCann | Yesmail | 11/1, 11/10, 11/22-11/27 | Sterling
Neil Arsenty | Yesmail | 11/10, 11/22 | Ravi, Dina
Diana Strandberg | Yesmail | 11/10, 11/22
Rachel Skolnick | Yesmail | 11/9, 11/10, 11/16,11/17 | Diana, Meghan
Sterling Crain | Yesmail | 11/28 - 11/30 | Afton, Stephani
December
Sterling Crain | Yesmail | 2017-12-01 | Afton, Stephani
Christina Chang | Yesmail | 12/4/2017, 12/26-12/27 | Sterling
Neil Arsenty | Yesmail | 12/1, 12/8 | Ravi, Dina
Diana Strandberg | Yesmail | 12/7-12/8, 12/15, 12/26
Rachel Skolnick | Yesmail | 12/5, 12/7, 12/13, 12/14, 12/15
Mimi Zhou | Yesmail | 12/26 -12/28
Dina Touchon | Yesmail | 12/27-12/28 | Ravi
Kaitlin Seger | Yesmail | 12/26-12/28 | Meghan, Mimi, Maureen
Neil Arsenty | Yesmail | 12/26 - 12/28 | Ravi (12/27-28), Dina (12/26)
Lisa Cannon | Marriott | Week of Christmas
Stephani Kuehn | Yesmail | Week of Christmas | Sterling, Afton
Leigh Strickland | Marriott | Week of Christmas
Erica Huntley | Marriott | 12/1, 12/21 | Marc
Erica Huntley | Marriott | 12/26, 12/27, 12/28 | Call Erica for escalation
Afton McCann | Yesmail | 12/27 AM
January
Kaitlin Seger | Yesmail | 1/2-1/4 | Meghan, Mimi, Maureen
Afton McCann | Yesmail | 2018-01-26 | Stephani, Christina, Jenna
Rachel Skolnick | Yesmail | 1/22-26 | Diana, Meghan, Mimi
Dina Touchon | Yesmail | 1/15 - 1/18 | Neil, Ravi
Meghan Monahan | Yesmail | 2018-01-29 | Mimi, Rachel, Diana
February
Erica Huntley | Yesmail | 2/1-2/2
Sabina/Francesca/Leigh | Marriott | 2/7 in meetings all day
Jenna Bresnahan | Yesmail | 2/5, 2/6 in meetings
Jen Tabbal | Yesmail | 2018-02-08 | Heather
Rachel Skolnick | Yesmail | 2/8, 2/16 | Diana, Meghan, Mimi
Mimi Zhou | Yesmail | 2/14 - 2/16, 2/20 | Diana, Meghan, Rachel
Lisa Cannon | Marriott | 2/19-2/26
Sabina Shehi | Marriott | 2018-02-20
Sabina, Francesca, Lisa | Marriott | 2/21 in meetings
Afton McCann | Yesmail | 2018-02-28 | Stephani, Christina, Jenna
March
Jenna Bresnahan | Yesmail | 3/9-3/15
Sabina and Francesca | Marriott | 3/13 and 3/20 (whole team) meetings all day
Diana Strandberg | Yesmail | 3/14-3/16
Christina Chang | Yesmail | 3/2, 3/15 (afternoon), 3/30 (afternoon) | Afton, Stephani, Jenna
Lisa Cannon | Marriott | 3/28-4/4
Stephani Kuehn | Yesmail | 3/28-3/29 | Christina, Jenna
Afton McCann | Yesmail | 3/26-3/30 | Stephani, Christina, Jenna
April
Neil Arsenty | Yesmail | 2018-04-02 | Dina, Ravi
Sabina Shehi | Marriott | 4/2 - 4/5
Afton McCann | Yesmail | 4/6, 4/13 | Stephani, Christina, Jenna
Jen Tabbal | Yesmail | 4/5 - 4/9 | Heather
Rachel Skolnick | Yesmail | 2018-04-06 | Diana, Mimi, Meghan
Brandon Scheiner | Yesmail | 4/12, 4/13 | Jun, Meegan, Larry
Stephani Kuehn | Yesmail | 4/13 (morning) | Jenna
Dina Touchon | Yesmail | 2018-04-13 | Neil, Ravi
Christina Chang | Yesmail | 4/13, 4/23 | Afton, Stephani, Jenna
Diana Strandberg | Yesmail | 2018-04-27
Marriott Team | Marriott | 2018-04-16
Lisa Cannon | Marriott | 4/19-4/23
Kerry Greene | Marriott | 4/23-4/25
May
Leigh Strickland | Marriott | 5/1-5/4
Diana Strandberg | Yesmail | 5/4 & 5/7
Meghan Monahan | Yesmail | 5/14 PM (1/2 day) | Diana, Rachel, Mimi
Rachel Skolnick | Yesmail | 2018-05-21 | Diana
Sabina Shehi | Marriott | 5/23-5/30
Jen Tabbal | Yesmail | 5/25 (1/2 day) | Heather
Brandon Scheiner | Yesmail | 5/23-5/29 | Jun, Meegan, Larry
Meghan Monahan | Yesmail | 5/24-5/31 | Diana, Mimi, Rachel
Stephani Kuehn | Yesmail | 5/24-5/25 | Afton, Jenna, Christina
Neil Arsenty | Yesmail | 5/29-5/31 | Dina, Ravi
June
Meghan Monahan | Yesmail | 2018-06-01 | Diana, Mimi, Rachel
Neil Arsenty | Yesmail | 6/1-6/6 | Dina, Ravi
Jen Tabbal | Yesmail | 2018-06-07 | Heather
Dina Touchon | Yesmail | 2018-06-13 | Neil, Ravi
Sabina Shehi | Marriott | 6/14-6/25
Marriott Team | Marriott | all-hands meeting 6/18-19
Christina Chang | Yesmail | 6/28, 6/29 | Afton, Stephani, Sterling
Lisa Cannon | Marriott | 6/25 - 6/29
Mimi Zhou | Yesmail | 6/28-6/29 | Diana, Meghan
Jen Tabbal | Yesmail | 2018-06-22 | Heather
Brandon Scheiner | Yesmail | 2018-06-22 | Meegan, Jun
July
Francesca Scutari | Marriott | 2018-07-02
Mimi Zhou | Yesmail | 7/2 -7/3, 7/5 -7/6 | Diana, Meghan
Dina Touchon | Yesmail | 7/5-7/6 | Neil, Ravi
Stephani Kuehn | Yesmail | 7/5, 7/13, 7/16 | Afton, Sterling, Christina
Erica Huntley | Yesmail | 7/9 - 7/13
Diana Strandberg | Yesmail | 2018-07-23
Christina Chang | Yesmail | 2018-07-23 | Afton, Stephani, Sterling
Dina Touchon | Yesmail | 2018-07-27 | Neil, Ravi
Afton McCann | Yesmail | 7/26 , 7/30 (design seminar) | Stephani, Christina, Sterling
Brandon Scheiner | Yesmail | 7/17 - 7/22 | Diane, Jun, Larry
Marriott Team Limited Availability | Marriott | 7/17 (all hands), 7/19 (Lacek/Epsilon training)
August
Meghan Monahan | Yesmail | 2018-08-03 | Diana, Mimi
Jen Tabbal | Yesmail | 8/3, 8/13 - 8/17 | Heather
Dina Touchon | Yesmail | 8/13-8/17 | Neil, Ravi
Afton McCann | Yesmail | 8/8-8/10 | Stephani, Christina, Jenna
Neil Arsenty | Yesmail | 8/17, 8/20 | Dina, Ravi
Stephani Kuehn | Yesmail | 8/27-8/31 | Afton, Sterling, Christina
Mimi Zhou | Yesmail | 2018-08-29 | Meghan, Maureen, Kaitlin
Sabina Shehi | Marriott | 8/23-27, 8/31
Dina Touchon | Yesmail | 8/27-8/31 | Neil
September
Afton McCann | Yesmail | 2018-09-10 | Stephani, Christina, Sterling
Eliza Kalm | Marriott | 9/3-9/7 (and 8/31)
Sabina Shehi | Marriott | 9/3-9/7
Meghan Monahan | Yesmail | 9/3-9/7 | Diana, Mimi, Kaitlin, Maureen
Kaitlin Seger | Yesmail | 9/7-9/10 | Diana, Mimi, Maureen
Christina Chang | Yesmail | 2018-09-07 | Afton, Stephani, Sterling
Dina Touchon | Yesmail | 2018-09-13 | Neil
Stephani Kuehn | Yesmail | 9/14 (afternoon) | Afton, Sterling, Christina
Sterling Crain | Yesmail | 2018-09-21 | Afton, Stephani, Christina
October
Mimi Zhou | Yesmail | 10/3 -10/12 | Diana, Meghan, Maureen, Kaitlin
Kaitlin Seger | Yesmail | 2018-10-08 | Diana, Mimi, Meghan, Maureen
Afton McCann | Yesmail | 10/8-10/11 | Stephani, Christina, Sterling
Christina Chang | Yesmail | 10/8, 10/15-19, 10/26-10/31 | Afton, Stephani, Sterling
Maureen Zigulich |  | 10/11- 10/15 | Meghan, Kaitlin
Sterling Crain | Yesmail | 10/22-10/31 | Afton, Stephani, TBD
December
Sterling Crain | YM | 12/10, 12/14, 12/20-12/21 | Stephani, Afton, Christina
Meghan Monahan | YM | 12/20-12/28 | Diana, Mimi, Maureen, Kaitlin
Kaitlin Seger | YM | 12/26 - 1/4 | Diana, Mimi, Meghan, Maureen
Neil Arsenty | YM | 12/26-12/28 | Dina, Ravi
Dina Touchon | YM | 12/20 1/2 afternoon and 12/21 | Neil, Ravi
Stephani Kuehn | YM | 12/17 afternoon, 12/19 afternoon | Afton, Sterling, Chrstina
Stephani Kuehn | YM | 12/26-12/28 | Afton, Sterling, Chrstina
Mimi Zhou | YM | 2018-12-28
Maureen Zigulich | YM | 2018-12-27 | Diana, Brittany, Mimi
Brittany Roeper | YM | 12/21 PM only
Brittany Roeper | YM | 2018-12-26
Jen Tabbal | YM | 12/26 - 12/28 | Dana, Heather
Afton McCann | YM | 12/7, 12/26 | Sterling, Stephani, Christina
Sabina Shehi | Marriott | 2018-12-14
Sabina Shehi | Marriott | 12/20-12/31
Erica Huntley | YM | 12/21, 12/26-12/28
Diana Strandberg | YM | 12/21, 12/26
January
Afton McCann | YM | 1/10-1/11, 1/16 (afternoon) | Sterling, Stephani, Christina
Kaitlin Seger | YM | 1/2 - 1/4 | Diana, Mimi, Meghan, Maureen
Brandon Scheiner | YM | 1/2 - 1/4 | Jun, Meegan
February
Meghan Monahan | YM | 2/7, 2/8 | Kaitlin, Mimi, Brittany
Kaitlin Seger | YM | 2019-02-22 | Meghan, Brittany, Mimi
March
April
Kaitlin Seger | YM | 2019-04-26 | Meghan, Brittany, Mimi
May
June
July
Meghan Monahan | YM | 7/29-31 | Kaitlin, Mimi, Brittany
August
Meghan Monahan | YM | 8/1-9 | Kaitlin, Mimi, Brittany
September
October
November
December

## Holidays
| Holiday | Marriott Holiday | Yesmail Holiday | Day of the Week
2018-12-31 | New Years Eve | yes | yes | Monday
2019-01-01 | New Years | yes | yes | Tuesday
2019-01-21 | Martin Luther King Day | yes | no | Monday
2019-02-18 | Washington's Birthday | yes | yes | Monday
2019-05-27 | Memorial Day | yes | yes | Monday
2019-07-04 | Independence Day | yes | yes | Thursday
2019-09-02 | Labor Day | yes | yes | Monday
2019-11-28 | Thanksgiving Day | yes | yes | Thursday
2019-11-29 | Day after Thanksgiving | yes | yes | Friday
2019-12-24 | Christmas Eve | yes | yes | Tuesday
2019-12-25 | Christmas | yes | yes | Wednesday
2019-12-31 | New Years Eve | yes | yes | Tuesday

## Retrofit Worksheet (hidden)
Timelines
Project # Design | Project # WP | 1.0 Project # Design & WP | Campaign | Campaign Production Support | Designer | WP | Impact | Versions | Version Info | Languages | Internal Stage | Status/Notes | Kickoff & Discovery | Internal Review | Client Presentation | Creative Kick-off | Design Internal Review | Design Review 1 | DR 1 Feedback | Design Review 2 | Design in-language version(s) due by EOD | DR 2 Feedback | Final Design Review | Approval | Translation Doc due (EM) by EOD | Link Matrix due by 11AM EST (CPS) | Coding | Functional QA | Hand-off | Asset Review Call | Test Launch | Feedback to Epsilon | Launch | NOTES | WP Hours - 3 WP Resources | QA Hours - Need 3 resources
|  |  | 1 version EN | [12 empty] | 2017-06-06 | 2017-06-08 | 2017-06-09 | 2017-06-09 | 2017-06-12 | n/a | 2017-06-13 | 2017-06-14 | 2017-06-14 | n/a | 2017-06-15 | 2017-06-15 | 2017-06-16 | 2017-06-19 | 2017-06-19 |  |  | 2017-07-01
|  |  | 1 version in-lang | [12 empty] | 2017-07-21 | 2017-07-25 | 2017-07-26 | 2017-07-26 | 2017-07-27 | 2017-07-27 | 2017-07-28 | 2017-07-31 | 2017-07-31 | 2017-07-28 | 2017-08-03 | 2017-08-03 | 2017-08-04 | 2017-08-07 | 2017-08-07 |  |  | 2017-08-25
|  |  | 2-3 versions EN | [12 empty] | 2017-05-30 | 2017-06-02 | 2017-06-05 | 2017-06-05 | 2017-06-06 | n/a | 2017-06-07 | 2017-06-08 | 2017-06-08 | n/a | 2017-06-09 | 2017-06-09 | 2017-06-12 | 2017-06-13 | 2017-06-13 |  |  | 2017-07-01
|  |  | 2-3 version in-lang | [12 empty] | 2017-05-22 | 2017-05-25 | 2017-05-26 | 2017-05-26 | 2017-05-29 | 2017-05-29 | 2017-05-30 | 2017-05-31 | 2017-05-31 | 2017-05-30 | 2017-06-06 | 2017-06-06 | 2017-06-08 | 2017-06-09 | 2017-06-09 |  |  | 2017-07-01
|  |  | 3-4 versions EN | [12 empty] | 2017-05-25 | 2017-05-31 | 2017-06-01 | 2017-06-01 | 2017-06-02 | n/a | 2017-06-05 | 2017-06-06 | 2017-06-06 | n/a | 2017-06-07 | 2017-06-07 | 2017-06-08 | 2017-06-09 | 2017-06-09 |  |  | 2017-07-01
|  |  | 3-4 version in-lang | [12 empty] | 2017-05-09 | 2017-05-15 | 2017-05-16 | 2017-05-16 | 2017-05-17 | 2017-05-17 | 2017-05-18 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-30 | 2017-05-30 | 2017-06-02 | 2017-06-05 | 2017-06-05 |  |  | 2017-07-01
Task Breakdown
OWNER | [12 empty] | AM/Strategy/Client | AM/Strategy/Design | AM/Strategy/Client | AM/Design | AM/Design | AM/Design/Client/Lacek | AM/Design/Client/Lacek | AM/Design/Client/Lacek | Design | AM/Design/Client/Lacek | AM/Design/Client/Lacek | AM/Design/Client/Lacek | EM | CPS | EM/WP | EM/WP | EM/WP/CPS/Epsilon | CPS/Epsilon | EM/WP/CPS/Epsilon | EM/WP/CPS/Client/Epsilon | CPS/Epsilon
Project # Design | Project # WP | 1.0 Project # Design & WP | Campaign | Campaign Production Support | Designer | WP | Impact | Versions | Version Info | Languages | Internal Stage | Status/Notes | Kickoff & Discovery | Internal Review | Client Presentation | Creative Kick-off | Design Internal Review | Design Review 1 | DR 1 Feedback | Design Review 2 | Design in-language version(s) due by EOD | DR 2 Feedback | Final Design Review | Approval | Translation Doc due (EM) by EOD | Link Matrix due by 11AM EST (CPS) | Coding | Functional QA | Hand-off | Asset Review Call | Test Launch | Feedback to Epsilon | Launch | NOTES | WP Hours - 3 WP Resources | QA Hours - Need 3 resources
TASK DETAILS | [12 empty] | 30 min call | 30 min call | 30 min call | 30 min call | Slack/Email | 15 min call | Given on call, or via email. AM team adds feedback to Message Tracker. | Delivered via email. | Design alerts team completed via email. | Delivered via email. | Delivered via email. | Delivered via email. | Google doc. | Google doc. | Hand-off call 15 min. |  | Delivered via email. All assets due at 3PM EST on due date. EM- delivers coded assets. CPS- delivers email creative, links, Job Ticket(s). | If needed 30 min call with Epsilon to discuss campaign build. | Delivered via email. | EM/WP/CPS: Feedback due from litmus review. CPS: Feedback due from test review including any feedback from Clark, Lacek, legal, and proofreading. | CPS approves launch via Job Ticket with Epsilon.
These steps only applicable to Full Strategy bucket campaign.

## CPS Retrofit Test Approval (hidden)
2.0 Design # | Campaign | CPS | Litmus | CPS | Clark | Legal | Proofreading | ADA Compliance Check | Lacek | Changes submitted | Launch
June (Batch 1)
MAR-0503 | Welcome Existing - EN | Rachel | x | x | x | x | x | x | x |  | 2017-06-28
MAR-0503 | Welcome Existing - CN, SP, FR, DE | Rachel | x | x | x | - | - | x | - |  | 2017-06-28
MAR-0503 | Welcome Existing - JP, BR, RU | Rachel |  |  |  | - | - |  | -
MAR-0504 | Welcome Double Opt-In - EN | Rachel | x | x | x | x | x | x | x | 2017-06-12 | 2017-06-28
MAR-0504 | Welcome Double Opt-In - CN, SP, FR, DE | Rachel | x | x | x | - |  | x | - | 2017-06-12 | 2017-06-28
MAR-0504 | Welcome Double Opt-In - JP, BR, RU | Rachel |  |  |  | - |  |  | -
MAR-0504 | Welcome Flipper - EN | Rachel | x | x | x | x | x | x | x |  | 2017-06-28
MAR-0505 | Welcome Flipper - EN, CN, SP, FR, DE | Rachel | x | x | x | - |  | x | - |  | 2017-06-28
MAR-0505 | Welcome Flipper JP, BR, RU | Rachel |  |  |  | - |  |  | -
MAR-0506 | Welcome NonMember - EN | Rachel | x | x | x | x | x | x | x | 2017-06-06 | 2017-06-28
MAR-0506 | Welcome NonMember - CN, SP, FR, DE | Rachel | x | x | x | - | - | x | - | 2017-06-06 | 2017-06-28
MAR-0506 | Welcome NonMember - JP, BR, RU | Rachel |  |  |  | - |  |  | -
MAR-0500 | Lifetime Achievers (Silver/Gold/Platinum) EN | Carley | x | x | x | x | x | x | x |  | 2017-06-28
MAR-0500 | Lifetime Achievers (Silver/Gold/Platinum) CN, SP, FR, DE | Carley | x | x |  | - |  | x | - |  | 2017-06-28
MAR-0500 | Lifetime Achievers (Silver/Gold/Platinum) JP, BR | Carley |  |  |  | - |  |  | -
MAR-0507 | Welcome Points (Welcome/EES1/EES2/EES3) EN | Rachel | x | x | x | x | x | x | x |  | 2017-06-28
MAR-0507 | Welcome Points (Welcome/EES1/EES2/EES3) CN, SP, FR, DE | Rachel | x | x | x | - | - | x | - |  | 2017-06-28
MAR-0507 | Welcome Points (Welcome/EES1/EES2/EES3) JP, BR, RU | Rachel |  |  |  | - | - |  | -
MAR-0508 | Welcome Miles (Welcome/EES1/EES2) EN | Carley | x | x | x | x | x | x | x |  | 2017-06-28
MAR-0508 | Welcome Miles (Welcome/EES1/EES2) CN, SP, FR, DE | Carley | x | x | x | - | - | x | - |  | 2017-06-28
MAR-0508 | Welcome Miles (Welcome/EES1/EES2) JP, BR, RU | Carley |  |  |  | - | - |  | -
MAR-0509 | Achievers (Silver/Gold/Platinum) EN | Carley | x | x | x | x | x | x | x |  | 2017-06-28
MAR-0509 | Achievers (Silver/Gold/Platinum) CN, SP, FR, DE | Carley | x | x |  | - | - | x | - |  | 2017-06-28
MAR-0509 | Achievers (Silver/Gold/Platinum) JP, BR | Carley |  |  |  | - | - |  | -
x
MAR-0510 | Renewers (Silver/Gold/Platinum) EN | Rachel |  |  | x | x | x |  | x |  | 2017-06-28
|  |  | x | x
MAR-0511 | Post Redemption (Restarters) - EN | Rachel | x | x | x | x | x | x |  |  | 2017-06-28
MAR-0511 | Post Redemption (Leftovers) - EN | Rachel |  |  | x | x | x | x |  |  | 2017-06-28
MAR-0512 | Abandon Search (Destination) - EN | Diana | x | x | x | x | x |  |  |  | 2017-06-28
MAR-0512 | Abandon Search (Hotel) - EN | Diana | x | x | x |  |  |  | x |  | 2017-06-28
x
MAR-0513 | Near Level (Silver/Gold/Platinum) EN | Carley | x |  |  | x | x | x |  |  | 2017-06-28

## TEMPLATE 2.0 (hidden)
Requestor |  |  |  |  | Request Date | Update Description | WP Assigned | Date Competed
Sterling Crain |  |  |  |  | 2017-07-24 | Adding secondary CTA option (text with arrow) Example: http://preview.4at5.net//email_domains/mar/164736/MAR-0562_NFLMomentsCampaign_164736_080817.html
Task | WP | MM | QA | Items needed | START DATE | END DATE | DURATION
Initial Build - English | 55 | 2 | 1.5 |  | 2017-03-14 | 2017-04-05 | ~ 3 weeks (3-4 hours/day)
Peer Review | 2 |  |  | Bill peer review | 2017-04-03 | 2017-04-03 | 1 day
Creative Review |  |  |  | Afton sign-off | 2017-04-03 | 2017-04-03 | 1 day
Revisions | 5 | 1.5 | 0 |  | 2017-04-04 | 2017-04-04 | 1 day
QA Rendering/links |  | 4 |  |  | 2017-04-05 | 2017-04-05 | 1 day
Revisions | 2 | 1 | 1 |  | 2017-04-06 | 2017-04-06 | 1 day
Handoff English | [5 empty] | 2017-04-07
Build - 7 languages | 14 | 2 | 14 |  | 2017-04-10 | 2017-04-10 | 1 day
Language QA |  |  |  |  | 2017-04-11 | 2017-04-12 | 2 days
Revisions/links | 7 | 2 | 0 |  | 2017-04-13 | 2017-04-13 | 1 day
Epsilon Hand-off | 2 | 1 |  |  | 2017-04-14 | 2017-04-14
Revisions (ongoing) | 10 | 10
Totals | 97 | 23.5 | 16.5 | 137

## Strat Timelines (hidden)
|  | MR/AM/STRAT | MR/AM/STRAT |  | STRAT-AM | STRAT | MR/STRAT/AM | MR | STRAT |  |  | MR |  |  | STRAT | MR/STRAT/AM |  | MR/STRAT | MR | MR | STRAT/DESIGN/AM | MR/AM/DES
Project # | Project | Kick-off | Discovery call | Check-In (as needed) | Internal Review | Campaign Strategy | Campaign Strategy Presentation | MR Feedback | Revised Brief | MR feedback | Final Brief | Approval | Internal Draft | Internal Feedback | Strategic Brief *Diana start managing here* | Strategic Brief Presentation | MR Review / Feedback | Revised Brief | Approval | Develop Project Brief | Internal Handoff | Creative Kick-off *Create timeline*
|  | 1 day | 1 day |  |  | 10 days | 1 day | 2 days | 2 days | 2 days | 1 day | 1 day |  |  | 5 days | 1 day | 3 days | 2 days | 1 day | 3 days | 1 day | 1 day
| eAppend - Reactivation Strategy | 2017-11-13 | 2017-11-20 |  | 2017-11-30 | 2017-12-04 | 2017-12-05 | 2017-12-07 | 2017-12-11 | 2017-12-13 | 2017-12-14 | 2017-12-15 | [7 empty] | 2017-12-19 | 2017-12-19 | 2017-12-20
MORE Marketing Plan
Moments Marketing Plan
MegaBonus Marketing Plan
|  | Discovery | Present | Data |  | Initial Build | Internal Review | MR Feedback | M&C Review | Present
|  | 2nd Thursday | 2nd Thursday | 5 biz days |  | 2 biz days | 5 biz days | 5 biz days | 5 biz days | 7 biz days
| May Monthly Email Review |  | 2016-07-07
| May Monthly PO Review |  | 2016-07-08
| June Monthly Email Review |  |  | 2016-07-15 | 2017-12-04: 2016-07-17; 2017-12-07: 8/4 present
| June Monthly PO Review |  |  | 2016-07-15 | 2017-12-04: 2016-07-17; 2017-12-07: 8/5 present
| MR Q4 Quarterly Planning | 2016-07-08 |  | 7/11 Internal Worksession; 7/14 Client Worksession | 2017-12-05: 7/22 internal review; 2017-12-07: 7/27 Marc/Clark Review; 7/29 feedback due; 2017-12-13: 2016-08-16
| MR Q2 Review |  |  |  | 2017-12-11: Write MR Quarterly Review, 8/12 Marc/Clark review; 2017-12-13: 2016-08-16
| PO Q2 Review |  |  |  | 2017-12-13: 2016-08-17
| August Monthly Email Review |  | 2016-10-06
| August Monthly PO Review |  | 2016-10-07
| September Monthly Email Review |  |  | 2016-10-15 | 2017-12-04: 2016-10-17; 2017-12-07: 11/3 present
| September Monthly PO Review |  |  | 2016-10-15 | 2017-12-04: 2016-10-17; 2017-12-07: 11/4 present
| MR Q1 Quarterly Planning | 2016-10-25 |  | 10/13 Client Work session | 2017-12-05: 10/21 Marc/Clark Review; 10/24 feedback due; 2017-12-13: 2016-11-17
| MR Q3 Review |  |  |  | 2017-12-11: 11/11 Marc/Clark Review; 2017-12-13: 2016-11-17
| PO Q3 Review |  |  |  | 2017-12-13: 2016-11-18
October Monthly Email Review
October Monthly PO Review
November Monthly Email Review
November Monthly PO Review
MR Q2 Quarterly Planning
MR Q4 Review
PO Q4 Review
December Monthly Email Review
December Monthly PO Review
2017 | bar: 2017-11-30 to 2017-12-13
| December Monthly Email Review |  | 2017-02-02 | kick off for Q2 quarterly planning
| PO Q4 Review |  | 2017-02-16
| MR Q4 Review |  | 2017-02-23
| MR Q2 Quarterly Planning |  | 2017-02-23
| January Monthly Email Review |  | 2017-03-02
| February Monthly Email Review |  | 2017-04-06
| MR Q1 Review |  | 2017-04-20
| MR Q3 Quarterly Planning |  | 2017-05-04
| MarchMonthly Email Review |  | 2017-05-02
| April Monthly Email Review |  | 2017-06-02
| May Monthly Email Review |  | 2017-07-06
| MR Q2 Review |  | 2017-07-20
| MR Q4 Quarterly Planning |  | 2017-08-03
| June Monthly Email Review |  | 2017-08-03
| July Monthly Email Review |  | 2017-09-07
| August Monthly Email Review |  | 2017-10-05
| MR Q3 Review |  | 2017-10-19
| MR Q1 Quarterly Planning |  | 2017-11-02
| September Monthly Email Review |  | 2017-11-02
| October Monthly Email Review |  | 2017-12-07
| MR Q4 Review |  | 2017-12-21
| MR Q2 Quarterly Planning |  | 2018-01-04
| November Monthly Email Review |  | 2018-01-04

## Recovered_Sheet1 (hidden)
Project | Lead Strat | Lead AM | Del Date | Description | Proj Hours | Ted's Notes
2015-02-01
Meeting 1 |  |  | 2015-02-04
- 2014 Q4 Review |  |  |  |  | 50
Meeting 2 |  |  | 2015-02-11 | Project Plan, Priorities & Search Box
- Search Box: Strategic Approach |  |  |  | Approved | 20
- Prioritize Strategy Deliverables |  |  |  |  | 10
Meeting 3 |  |  | 2015-02-18
- VOR Feedback/Priorities |  |  |  |  | 10
Meeting 4
Q3 Quarterly Planning |  |  | 2015-02-25 |  | 50
2015-03-01
QBR Washington D.C. |  |  | 3/16-3/17
- Concierge Discovery, Landing Page Brief |  |  |  |  | 25
-January Review |  |  |  |  | 40
- Member Experience Innovation Worksession |  |  |  |  | 50
-Year in Review deep dive and recommendations |  |  |  |  | 15
- Learning Agenda Review |  |  |  |  | 5
Wylei Meeting |  |  | 2015-03-24 |  | 10
--Program Roadmap Review |  |  |  |  | 5
2015-04-01
Meeting 1 |  |  | 2015-04-02
February Review |  |  |  |  | 40 | May be able to do an analysis here
--YIR Post-Mortem/Mid-Year Discovery |  |  |  |  | 5
--Review Project Plan/Roadmap |  |  |  |  | 5
Meeting 2 |  |  | 2015-04-20
--Mid-Year in Review Campagin Brief Check-in |  |  |  |  | 30
Meeting 3 |  |  | 2015-04-30
--Mid-Year in Review Campagin Brief Delivery |  |  |  | MR team reviewing 5/5 | 25
2015-05-01
Project Orange Planning Session |  |  | 2015-05-07 | Determine approach for July - Dec
Meeting 1 |  |  | 2015-05-07
--Q1 Review |  |  |  |  | 50
--Project Orange regroup
Meeting 2 |  |  | 2015-05-13
--Monthly Strategy meeting |  |  |  | Review Roadmap
Meeting 3 |  |  | 2015-05-28
--April Review |  |  |  |  | 40
--Points Expiration Discovery |  |  |  |  | 15
--Q1 Review w/ Lynne |  |  |  |  | 10
2015-06-01
Meeting 1 |  |  | 2015-06-10 | In Person
--Q4 Quarterly Planning |  |  |  |  | 50
Email Roadshow Deck |  |  | 2015-06-16
Points Expiration Brief Delivery |  |  | 2015-06-18 |  | 16
Meeting 2 |  |  | 2015-06-24
--May Review |  |  |  |  | 40
--Internal Email Evangilization |  |  | TBD | Email Process | 10
-- YIR Discovery |  |  | 2015-06-30
2015-07-01
Meeting 1 |  |  | 2015-07-16 | Move to July 16th
--YIR Solo Strategy Check-in |  |  |  |  | 30
--Welcome Series Launch Analysis |  |  |  | Analysis of Welcome series (attn: to points) |  | CC will get back to us on next steps
--Elite Off Track Analysis | [5 empty] | Kerry is reviewing on her own
New: MRCC Redesign Strategy |  |  |  |  | 10 | Replace Abandon Search
New: Project Orange Reporting | [5 empty] | Need head to head comparison against standard campaign
2015-08-01
-- Preview Q2 Review with Marc/Clark |  |  | 2015-08-03
QBR |  |  | Aug. 6-7
--Q2 Review |  |  |  |  | 60
--YIR Brief Delivery |  |  |  |  | 35
--Welcome Series Cont. |  |  |  |  | 10
--Commemorative Message Recos |  |  |  | Discussion provide recos
Meeting 2 |  |  | 2015-08-12
--MRCC Redesign Strategy Discovery |  |  |  |  | 25
--Q2 Review for Lynne
--Status Update of QBR
Meeting 3 - NYC |  |  | 2015-08-19
2015-09-01
--YIR Campaign Worksession |  |  | 2015-09-03 |  |  |  | Overall, move deliverables to Sept 9th for July review, MRCC Redesign check-in, and roadshow....
Meeting 1 |  |  | 9/10 -9/11 | In person |  |  |  | Travel Personality support | 3 | Asap
--YIR internal presentations
--July Review |  |  |  |  | 50 |  | Resource can help... | Quiz development support | 3 | Asap
--NEW: Commemorative Messaging Solo
--MRCC Redesign Strategy Check-in |  |  | 2015-09-16 |  |  |  |  | MR internal roadshow |  | Around Labor Day
--MRCC Redesign Strategy Delivery |  |  | 2015-09-24 |  | 20 |  |  | Creative + Social | 3
--YIR Lynne / Thom |  |  | 2015-09-29 |  | 50 |  | Deprioritize (Account module more important) | Project Orange | 3
--August Review |  |  | 2015-09-30 |  | 40 |  | Deprioritize | Lynne & Tom | 4
2015-10-01
Pre-Discovery w/Clark |  |  | 2015-10-08 |  | 4 | [5 empty] | Oct 2nd or Oct 5th, clark in town | bryan busy w/0 14th, 29th no good | Account Manager? Dial-in
Q1 '16 Quarterly Planning (at Marriott) |  |  | 2015-10-08 |  | 50
.Mic meeting |  |  | 2015-10-14
Data for 11/6 email discussion with Lynne & patty |  |  | 2015-10-15
Account Module Inputs Recommendation (phone) |  |  | 2015-10-16
Q3 Review |  |  | 2015-10-29 |  | 40
2015-11-01
1/2 Day for Lynne, VOR Discovery |  |  | 2015-11-06 | Bryan | [6 empty] | touchbase with Marc - spend day at Marriott, full day, Lynne to do half day | Bryan
Incent Redemption Strat Brief |  |  | 2015-11-17
VOR Worksession |  |  | 2015-11-19 | Bryan | 50
2015-12-01
October Review |  |  | 2015-12-03
VOR Worksession #2 |  |  | 2015-12-03
VOR Preview |  |  | 2015-12-18
2016-01-01 | [7 empty] | Ongoing topics of discussion
VOR Feedback due |  |  | 2016-01-04 |  |  |  |  | How to communicate Member rate
PBR Postponed |  |  | 1/25-1/26 |  |  |  |  | - Update all non member touchpoints (Nonmember welcome, dynamic content in eNews/Benefits, Social)
February
VOR, KPIs & Roadmap Review |  |  | 2016-02-11 |  |  |  |  | SPG communication opportunity
Q2 Planning |  |  | 2016-02-11
March | [7 empty] | Refer a friend (part of acquisition initiative)
PBR: 2015 Review/Focus on Q4 |  |  | 3/3 - 3/4
PBR: VOR Presentation to team |  |  | 3/3 - 3/4
PBR: Januray Review |  |  | 3/3 - 3/4
2nd Stay Nonmember Strategy Discovery |  |  | 2016-03-10
PO January Review |  |  | 2016-03-11
2016 Learning Agenda Update |  |  | w/o 3/21
April
Wylei / Jeff Data Meeting |  |  | 2016-04-06
February Review |  |  | 2016-04-06
PO February Review |  |  | 2016-04-08
Q3 Planning Kick-Off w/MR |  |  | 2016-04-15 | Question on ACQ Plan, Merger Re-Brand
Learning Agenda Updates
eBreaks Marketing Plan
May
Learning Agenda Updates |  |  | 2016-05-13
eBreaks Marketing Plan |  |  | 2016-05-13
March Review |  |  | 2016-05-05
PO March Review |  |  | 2016-05-06
Q3 Planning |  |  | 2016-05-12 | July eNews Kicks-off May 13
Q1 Review w/Lynne |  |  | 2016-05-13
PO Q1 Review |  |  | 2016-05-20
Learning Agenda Updates
June
April Review |  |  | 2016-06-02
PO April Review |  |  | 2016-06-14
Program Learning Summary deck |  |  | 2016-06-24
Template Testing Deck |  |  | 2016-06-24
July
May Review |  |  | 2016-07-07
Alliance and New Benefit Lifecycle Updates |  |  | 2016-07-07
Q4 Planning Kick-Off/Discovery |  |  | 2016-07-08
PO May Review |  |  | 2016-07-08
Q4 Planning Worksession |  |  | 2016-07-14
Client Review of Quarterly Plan |  |  | 2016-07-27
August
June Review |  |  | 2016-08-04
PO June Review |  |  | 2016-08-05
Client Preview of Quarterly Review |  |  | 2016-08-12
Q4 Planning |  |  | 2016-08-16 | Oct eNews kicks off 8/15
Q2 Review |  |  | 2016-08-16
PO Q2 Review |  |  | 2016-08-17
September
July Review |  |  | 2016-09-08
PO July Review |  |  | 2016-09-09
PBR: YLM Session: Consumer Trends |  |  | 2016-09-21
PBR: Template Refresh: High-level testing strategy/roadmap |  |  | 2016-09-21
PBR: YIR/Holiday Campaign Work Session |  |  | 2016-09-21
October
August Review |  |  | 2016-10-06
PO August Review |  |  | 2016-10-07
Q1 '17 Planning Discovery |  |  | 2016-10-25
Holiday Campaign |  |  | 10/ | Deliverable TBD
Mobile Strategy |  |  | 2016-10-01 | Understand Linkage rules, pathways... |  | trying to document as is.... share with clark 10/1 then mobile team w/o 11/14
Learning Agenda Review |  |  | 10/
November
September Review |  |  | 2016-11-03
PO September Review |  |  | 2016-11-04
Onboarding Link Analysis |  |  |  | 30 |  | 2 workstreams
Q1 '17 Planning Worksession |  |  | 2016-11-17 | Jan eNews kicks off 11/11 or before
Q3 Review |  |  | 2016-11-17 | Ok Bryan
PO Q3 Review |  |  | 2016-11-18 | Ok Bryan
December
Q1 '17 Plan |  |  | 2016-12-01
October Review |  |  | 2016-12-01
PO October Review |  |  | 2016-12-02
Mobile Strategy |  |  | 2016-12-09
2017 KPI Forecast |  |  | 2016-01-05 |  | 20-30
Learning Library |  |  | 2016-12-16 |  | 40-50
2016
Template Re-Brand Re-design |  |  | 2016
Welcome Series Re-design |  |  | 2016
Need to Prioritize
Nov PO review |  |  | 2017-01-12
EMIL KPI forecast (pro forma) |  |  | 2017-01-20
Wylei Recommendation |  |  |  | tbd
Communicatinos architecture click in |  |  |  | Waiting on meeting to discuss
30 Days deep dive |  |  |  | Waiting on due date and owner
Dec Review |  |  |  | scheudled 1/2
Q4 Review |  |  |  | needs to be scheduled mid Feb
PO Q4 Review |  |  |  | needs to be scheduled mid Feb
Subject Line learning agenda |  |  |  | need kick off with Jess
Learning Library update
Reviewer's Content Discussion
Booking Cycle Content Module Planning
Commerative Message Solos Discovery |  |  |  | Need to define # of Solos, scope of work in QBR session |  | Nice to have, don't need | Deprioritize
Early Activation Strategic Brief Discovery |  |  |  | post onboarding | 20-25
Early Activation Strategic Brief Check-in / Delivery |  |  |  | post onboarding | 20-25
Lifetime Achiever Brief Discovery |  |  |  | Adding new segment to Achiever brief
Lifetime Achiever Brief Delivery |  |  |  |  | 20
Analysis
Near Threshold/Achievers/Renewers Analysis |  |  |  | Move back | 20
BuyBack Analysis and Optimiazation |  |  |  | Not important, can't influence | 10 | Hand-off to someone else
PostRedemption Deep Dive analysis |  |  |  | Analysis of the three segmented emails for learning/optimization | 16 | Hand-off to someone else
Win Back/Hello Again Analysis
2017
Monthly Review: January | Ted |  | 2017-03-09
Megabonus Deep Dive Analysis | Erica
[PBR] Quarterly planning - 2017 plan | Ted
30-day Campaign Analysis | Ted | Diana |  | diana following up with Ivy
[PBR] Trends in Design / Cool stuff | Bryan
[PBR] Monthly Review: Feb | Ted |  | 2017-04-06
[PBR] Wylei Program Strategy | Erica | Diana |  | meeting
Hotel Specials Optimzation Recommendations | Erica | Diana |  | finalize next steps with key dates - funding discussion 4/19
Traveler NL: VOR - Opportunities Work Session | Erica | Edan | 2017-05-17

## Scheduling (hidden)
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!

## Subject Lines (hidden)
Project # | Campaign | Launch | Subject Line
Automated
MAR-0167 | Achievers In-language
MAR-0180 | Onboarding Series
MAR-0189 | Free Night Certificate
MAR-0068 | Reactivation
MAR-0059 | Early Engagement
MAR-0081 | Taste of Gold
MAR-0212 | Early Engagement PO Refresh - Solo | 2015-08-18
MAR-0215 | Points Expiration | 2015-11-01
August
MAR-0165 | Concierge August - Week 1 | 2015-08-03 | 5 Coastal Towns For Surfing (see #4)
MAR-0165 | Concierge August - Week 2 | 2015-08-10 | See Sandusky This Summer + Weekend Deals
MAR-0165 | Concierge August - Week 3 | 2015-08-17 | This Alabama Hotel Made T+L Top 500
MAR-0165 | Concierge August - Week 4 | 2015-08-24 | 3 September Events + Weekend Deals
MAR-0165 | Concierge August - Week 5 | 2015-08-31 | 5 Destinations Perfect For Labor Day
MAR-0190 | PO Benefits Email - August (enews) | 2015-08-04 | Your Account: Go More Places This Summer (TSAT)
Your Account: Get Your 5th Night Free (WHPH)
MAR-0175 | Silver Focus Points | 2015-08-06 | Register and earn up to 50,000 bonus points
MAR-0182 | eNews August | 2015-08-04 | Your Account – Get the 5th Night Free
MAR-0211 | Duplicate Email Solo | 2015-08-05 | Do We Have Your Correct Email Address?
MAR-0191 | PO Destination Email - August | 2015-08-11
MAR-0193 | MegaBonus Preview Solo | 2015-08-11 | Register for MegaBonus® on August 19
MAR-0210 | ECM Newsletter Q3 | 2015-08-18 | Your Cardmember Experience – Exclusive Program Offers and News
MAR-0183 | MRCC August | 2015-08-18
MAR-0194 | MegaBonus Announce Solo (English) | 2015-08-21 | Register for MegaBonus®, earn up to 20,000 points (dynamic offer specific language)
MAR-0194 | MegaBonus Announce Solo (in-language)
MAR-0192 | PO Offers Email - August (hs) | 2015-08-25 | [101] Travel Experiences Just for You (TSAT)
[101] Ways to Upgrade Your Travel (WHPH)
MAR-0184 | Hotel Specials August | 2015-08-25 | [101] Travel Deals You'll ♥
September
MAR-0165 | Concierge September - Week 1 | 2015-09-07 | This U.S. City Has The Most Food Trucks
MAR-0165 | Concierge September - Week 2 | 2015-09-08 | Work Hard, Play Harder in Chicago
MAR-0165 | Concierge September - Week 3 | 2015-09-09 | 6 Reasons to Visit Vermont
MAR-0165 | Concierge September - Week 4 | 2015-09-10 | 3 Events For Your October Calendar
MAR-0195 | PO Benefits Email - September (enews) | 2015-09-01 | Your Account – Experience MegaBonus® // Your Account – Your Private Villa is Ready (TSAT)
Your Account – MegaBonus® is Here // Your Account – Take Your Calls Poolside (WHPH)
MAR-0196 | eNews September | 2015-09-01 | Your Account: Redeem Around the World
Your Account: Your MegaBonus is Here
MAR-0216 | ShopMarriott INTL | 2015-09-04 | You Could Be the Winner!
MAR-0197 | PO Destination Email - September | 2015-09-15 | When is the Best Season to Visit Europe? (TSAT)
3 Tips to Stay Connected in Europe (WHPH)
MAR-0198 | Elite Off Track Solo | 2015-09-24
MAR-0199 | MRCC September | 2015-09-22 | [FNAME, ]Achieve Gold Elite Status + Earn 70,000 Bonus Points
MAR-0214 | MegaBonus Reg Reminder Solo | 2015-09-25
MAR-0200 | PO Offers Email - September (hs) | 2015-09-29 | We've Picked These Deals Just for You (TSAT)
How to Earn Points & Influence People (WHPH)
MAR-0201 | Hotel Specials September | 2015-09-29 | SL test
October
MAR-0188 | Concierge October - Week 1 | 2015-10-05 | 5 Gorgeous Ways to Experience Fall
| Concierge October - Week 2 |  | Vote for the Craziest Sports City
| Concierge October - Week 3 |  | Which November Festival is Best for You?
| Concierge October - Week 4 |  | What Your Favorite Candy Says About You
MAR-0202 | PO Benefits Email - October (enews) | 2015-10-06 | Your Account – MegaBonus®, Just for You
Your Account – We Picked These for You
MAR-0231 | Points Benefits Solo | 2015-10-13 | Big Changes are Coming...
MAR-0203 | eNews October | 2015-10-06 | Your Account: Rake in Points this October
Your Account: It's MegaBonus® Time
Your Account: Double Points – No Trick, Just Treat
MAR-0217 | MRCC October Extra Campaign UK&US | 2015-10-09
MAR-0204 | PO Destination Email - October | 2015-10-13
MAR-0218 | Atlantis Segments Solo | 2015-10-16 | It's Currently [84] Degrees at Atlantis
Jacket Weather? Not at Atlantis
MAR-0206 | NFL Solo | 2015-10-30
MAR-0207 | MRCC October | 2015-10-20 | [FNAME, ]Achieve Gold Elite Status + Earn 70,000 Bonus Points
MAR-0213 | MRCC October- Cardholder Design
MAR-0219 | ShopMarriott Cyber Monday Solo | 2015-10-20
MAR-0208 | PO Offers Email - October (hs) | 2015-10-27
MAR-0209 | Hotel Specials October | 2015-10-27
MAR-0220 | Mobile Request Solo | 2015-10-30 | We're at Your Service, Anytime
November
MAR-0188 | Concierge November - Week 1 | 2015-11-02 | Shh! 5 Secret Wine Trails
MAR-0188 | Concierge November - Week 2 | 2015-11-09 | 5 Reservation-Worthy Restaurants
MAR-0188 | Concierge November - Week 3 | 2015-11-16 | Got Vacation Days? 3 Ways to Spend Them
MAR-0188 | Concierge November - Week 4 | 2015-11-23 | 5 Trips Inspired by Thanksgiving Shows
MAR-0188 | Concierge November - Week 5 | 2015-11-30 | Do You Travel With These?
| PO Benefits Email - November (enews) | 2015-11-03
| eNews November | 2015-11-03
| Holiday Redemption | 2015-11-10 | Use Points. Get Gifts.
| PO Destination Email - November | 2015-11-10
| MRCC November | 2015-11-17
| PO Offers Email - November (hs) | 2015-11-24
| Hotel Specials November | 2015-11-24
December
MAR-0188 | Concierge December - Week 1-4 | 2015-10-05
| PO Benefits Email - December (enews) | 2015-12-01
| eNews December | 2015-12-01
| Mr. Marriott Solo | 2015-12-04
| MRCC December | 2015-12-08
| PO Offers Email - December (hs) | 2015-12-15
| Hotel Specials December | 2015-12-15
| Year in Review Solo | 2015-12-29

## Completed Strat Proj Plan (hidden)
Project | Del Date | Notes/Next Steps | Internal Notes | Proj Hours
2014-05-01 | Date
Q1 Review | 2014-05-01
Near Threshold & Achievers Campaign Strategy | 2014-05-14
Monthly Strategy Meeting | 2014-05-14
Aug eNews Content Strategy | 2014-05-28
Q4 Quarterly Planning: Discovery & Analysis | 2014-06-03
April Review | 2014-06-02
Flash Perks Support | tbd
2014-06-01
Monthly Strategy Meeting | 2014-06-11
May Review | 2014-06-24
Reporting Project | 2014-06-24
2014-07-01
Sep Content Strategy | 2014-07-01
Hotel Special Presentation | 2014-07-08 | Feedback: 8/30 | Larger discussion - likely will not have feedback this week
Onboarding Campaign Strategy | 2014-07-09 | Feedback - w/o 7/28 | Feedback 7/15 or following week
Q4 Quarterly Planning: Strategy | 2014-07-09 |  | Feedback 7/15 or following week
Test & Learn strategy roadmap | 2014-07-25 |  | Ted: updated name, let's call it this moving forward
Oct eNews Content Strategy | 2014-07-30
Q2 Quarterly Review | 2014-07-31
Birthday update discovery Call | 2014-07-31 | schedule
2014-08-01
Hotel Specials Evolution: Strategic Brief | 2014-09-03 | feedback-approval
Post Redemption | 2014-08-13 | feedback 8/20/ delivered 8/25 | discovery 8/7
Onboarding: Strategic Brief | 2014-08-13 | feedback (mid to end of Sept)
Monthly Strategy Meeting | 2014-08-13 |  | Birthday email Campaign Strategy, Strategic Assessment Work Session
Birthday Update: Campaign Strategy | 2014-08-27 | Creative Brief Review
December Year in Review: Kick-off | 2014-08-27 |  | need client direction on what will work in eNews vs Solo / Kick Off: to prep creative
Reporting Project Update | 2014-08-13 | update on progress (ongoing) | Discuss Strategic Assessment update with clark
July Review | 2014-08-27
Nov eNews Content Strategy | 2014-08-27
Test Plan Brief |  | this may be recurring, no specific need at this point | This is effectively the Test plan version of a strategic brief. Not sure if it belongs here yet so maybe don't show it
2014-09-01
Q1 '15 Quarterly Planning: Discovery & Analysis | 2014-09-10
Learning & Optimization Agenda Check-In | 2014-09-10
Monthly Strategy Meeting | 2014-09-10
Hello Again & Hello Again Reminder: Kick-off | 2014-09-15
Win-Back: Kick-off | 2014-09-15
Spring MegaBonus: Check-in | 2014-09-16
December Year in Review: Check-In | 2014-09-16
Q1 '15 Quarterly Planning: Strategy | 2014-09-29
December Year in Review: Vision | 2014-09-29 | final approval - creative kick-off
Spring MegaBonus: Strategic Brief | 2014-09-29 | presentation 10/16
Recommendation Tracking | 2014-09-29
2014-10-01
Hello Again: Strategic Brief | 2014-10-07 | approved
Pre Redemption: Strategic Brief | 2014-10-16
August Review | 2014-10-15
Monthly Strategy Meeting | 2014-10-15
Member Anniversary: Kick-off | 2014-10-15
Jan eNews Content Strategy | tbd
Q3 Quarterly Review | 2014-10-30 | schedule
2014-11-01
Member Anniversary Strategic Brief: Discovery | 2014-11-11 |  |  | 0.5
Monthly Strategy Meeting | 2014-11-12 |  | connect with clark on vision/opportunities | 1.5
Q2 Quarterly Discovery & Analysis | 2014-11-12 |  | 1 hour | 50
Vision & Opportunities Update: Proj Plan | 2014-11-12 | Share project plan and confirm dates |  | 40
Hotel Specials Evolution: Strategic Brief | 2014-09-03 | feedback-approval
Win Back: Strategic Brief | 2014-10-07 | feedback/approval
Member Anniversary Strategic Brief: Presentation | tbd |  |  | 25
Vision & Opportunities Update: Discovery | 2014-11-19 | confirm date & TT's availability | 11/18-11/20 1 hour - over the phone Clark & Terrilyn
Vision & Opportunities Update: Midpoint checkin | 2014-12-03 | confirm date & location | 12/2-12/4
Monthly Strategy Meeting |  | move to 12/16 or 12/17 |  | 1.5
Vision & Opportunities Update: Presentation | 2014-12-16 |  |  | 50
2015-01-01
Monthly Strategy Meeting | 2015-01-21 |  |  | 1.5
Q2 Quarterly Strategy Presentation | 2015-01-21 |  |  | 40
Vision & Opportunities Update: Roadmap | w/o 1/26 | VOR feedback and priorities |  | 50
Q4 Review | 2015-02-04 | Includes Oct-Dec Monthly | schedule for end of month | 65

## Completed Strategy (hidden)
|  |  |  | MR/AM/STRAT | MR/AM/STRAT | STRAT | MR/STRAT/AM | MR/STRAT | MR | STRAT | MR/STRAT/AM | MR/STRAT | MR | MR | STRAT | STRAT/DESIGN/AM
Project # | Campaign | Marriott Project Owner | Notes/Status | Kick off / Project request | Discovery call | Campaign Strategy | Campaign Strategy Presentation | Review & Feedback | Approval | Strategic Brief | Strategic Brief Presentation | Review & Feedback | Approval | Develop Project Brief | Strategy Review | Internal Handoff
|  |  |  | 1 day | 1 day | 10 days | 1 day | 8 days | 1 day | 5 days | 1 day | 5 days | 1 day | 5 days | 2 days | 1 day
MAR-0026 | Renewer's Automated Campaign | Kerry Mealia | Strategic Brief approval needed | 2014-11-12 | 2014-11-12 | n/a | n/a | n/a | n/a | 2014-12-16 | 2014-12-19 | 2014-01-31 |  | 2014-03-05 |  | 2014-03-07
MAR-0024 | Concierge Program | Jaya / Clark |  | 2014-03-06 | 2014-03-06
MAR-0045 | Welcome Email Series | Kerry Mealia | review porject briefs | 2014-01-30 | 2014-02-05 | n/a | n/a |  |  |  |  | n/a | 2014-02-26 | 2014-02-27 | 2014-03-25
MAR-0024 | Concierge Program | Jaya / Clark | audience reccommendations | 2014-03-06 | 2014-03-06
| Hotel Specials Analysis | Clark
| Marriott Rewards 2.0 | Kerry / Clark
| Birthday Update | Clark
| Abandon Search | Amy Anspach | will be with creative kick-off
Program for brand development
MAR-0065 | Near Threshold & Achievers | Kerry / Clark | approval - Proj Brief 6/19 | 2014-05-01 | 2014-05-05 | 2014-05-13 | 2014-05-14 | 2014-05-14 | 2014-05-16 | 2014-06-02 | 2014-06-05 | 2014-06-13 | n/a | n/a | n/a | n/a | 2014-06-19 | 2014-06-20 | TBD
MAR-0089 | eNews September | Lisa Cannon | Edan | Afton | Megan | brandon | Megan | litmus tests 8/27 | 2014-07-03 | 2014-07-10 | 2014-07-28 | 2014-07-29 | 2014-08-01 | 2014-08-01 | 2014-08-01 | 2014-08-04 | 2014-08-06 | 2014-08-08 | 2014-08-11 | 2014-08-12 | 2014-08-13 | 2014-08-14 |  | 2014-08-15 | 2014-08-19 | 2014-08-28 | 2014-09-01 | 2014-09-09 | 160552 | Brandon & Veronica | Litmus test - sent to QA
MAR-0092 | Post-Redemption | KC/CK/CC | Strat Brief 8/13 |  | 2014-08-08 | n/a | n/a | n/a | 2014-07-03: n/a; 2014-07-10: n/a; 2014-07-28: n/a; 2014-07-29: n/a; 2014-08-01: 2014-08-13; 2014-08-01: 2014-08-13
MAR-00 | Birthday Update* | Kerry / Clark | Creative Brief Review | n/a | 2014-07-31 | 2014-08-26 | 2014-08-27 | 2014-09-05 | 2014-08-01: n/a; 2014-08-04: n/a; 2014-08-08: n/a; 2014-08-11: n/a; 2014-08-12: 2014-09-04; 2014-08-14: 2014-09-09
MAR-00 | Year in Review - Solo & eNews | Lisa / Clark |  | 2014-08-27 |  | 2014-09-16 | 2014-09-29 | 2014-09-29 | 2014-07-03: 2014-10-07
MAR-00 | Spring MegaBonus | CC/LC/CK | presentation 10/16 | 2014-09-05 |  | 2014-09-16 | 2014-09-30 | 2014-09-30 | 2014-07-03: 2014-10-07
MAR-00 | Hello Again & Hello Again Reminder* | Kerry | approved | 2014-09-17 | 2014-09-19 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2014-09-30 | 2014-10-01 | 2014-10-03 | 2014-10-06 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-15 |  | 2014-10-15
MAR-00 | Pre-Redemption | KC/CK/CC | approved | n/a | 2014-09-28 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  |  | 2014-10-15 | 2014-10-15 | 2014-10-20 | 2014-10-22 | 2014-10-23 | 2014-10-28 |  | 2014-10-29
MAR-00 | Member Anniversary | Kerry | discovery 11/11 | n/a | 2014-11-11 |  | n/a | n/a | 2014-07-03: n/a; 2014-07-10: n/a; 2014-07-28: n/a; 2014-07-29: n/a; 2014-08-01: n/a
MAR-00 | Hotel Specials Evolution | Kerry / Clark | final feedback/approval | 2014-05-26 | 2014-06-11 |  | 2014-07-08 | 2014-07-08 | 2014-08-04: 2014-09-03; 2014-08-06: n/a
MAR-00 | Win Back | Kerry | feedback/approval | 2014-09-17 | 2014-09-19 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 2014-09-30 | 2014-10-01 | 2014-10-03 | 2014-10-06 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-16 |  | 2014-10-20
| Mid-Year in Review | Lisa / Clark | revisions 5/11 |  |  |  |  | 2015-04-30 | 2014-07-03: 2015-05-01; 2014-07-10: 2015-05-04; 2014-07-28: 2015-05-07; 2014-07-29: 2015-05-11; 2014-08-01: 2015-05-11; 2014-08-13: 2015-05-05 | 2015-05-06

## Deleted Campaigns (hidden)
MAR-0392 | 137650 | Cyber Monday Solo |  | Neil | Neil/Ashwini | z-Not Started | English only timeline | n/a | n/a | 2016-10-19 | 2016-10-20 | 2016-10-21 | 2016-10-25 | 2016-10-26 | 2016-10-28 | 2016-11-01 | 2016-11-03 | 2016-11-07 | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-14 | 2016-11-16 | 2016-11-25
MAR-0348 | 127347 | Travel List Solo | N/A |  |  | On Hold | Remove if not on CC's latest calendar please. | n/a | n/a

## DATA (hidden)
ART DIRECTORS | DESIGNERS | STATUS | COPY | AM | WEB PROD | PRIORITY | LEVEL
Unassigned | Unassigned | z-Not Started | Unassigned | Unassigned | Unassigned | High | Simple
Mike | Afton | Planning | Megan O | Edan | Brook | Medium | Medium
Matt | Mike | Strategy | Shannon | Lisa | Karrie | Low | Complex
Afton | Matt | Wireframe |  |  | Brenna |  | Redesign
| Ryan | MO |  |  | Brandon
| Alyson | Copy
| Jun | Design
| Diego | Design Revs
| Lauren | Client-Design
Client-WP
Web Prod
QA
Web Prod Revs
Translation
Epsilon Test
Epsilon Retest
Completed
On Hold