{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["On-Target Timeline"],"not_rendered":{"images":1,"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"On-Target Timeline","index":0,"n_rows":28,"n_cols":22,"rows_kept":28,"merged":[[3,2,3,14],[8,11,9,13],[8,14,9,14],[8,17,8,21]],"flags":["formulas_cached_only"]}
[]
[]
[null,null,"Ongoing Timeline:  Ritz Interactive (Templatizer)"]
[null,null,"Note: This 1-page document is a prioritized list of current On-Target eMessaging tasks.  The purpose of this document is to provide everyone with a quick glance at the sequence of events that @Once or the Client are responsible throughout the On-Target eMessaging process."]
[]
[{"$nulls":3},"Last Updated:","9/9/02"]
[]
[{"$nulls":4},"SUMMARY OF ON-TARGET TASKS:"]
[{"$nulls":4},"Tasks Remaining:",9,"Active Tasks:",0,null,"Tasks Waiting:",0,"# of Tasks in Waiting:",null,null,0]
[{"$nulls":4},"Tasks Completed:",0,"Planned Tasks:",9]
[]
[null,null,"REF","Entry Date","On-Target Task/Activity","Activity\nType","Phase","Status","Target Start Date","Due Date","LEAD","Sales Rep","AE","WD","Data Owner","Tech Owner","Other Tech Resources","Community Size","# of Rules","# of Msg Products","DATE COMPLETED","Notes & Actions"]
[null,null,"RITZ-001","2002-08-01","Content Submitted by Client:  CUF & Images","Content","On-going","PLANNED",null,"2002-09-06","CLIENT","MH","KM","MG","JF","RW"]
[null,null,"RITZ-002","2002-08-01","Data Submitted by Client: ","Data","On-going","PLANNED",null,"2002-09-06","AE","MH","KM","MG","JF","RW"]
[null,null,"RITZ-003","2002-08-01","@Once Tech QA","QA","On-going","PLANNED","2002-09-09","2002-09-09","AE","MH","KM","MG","TT","RW"]
[null,null,"RITZ-004","2002-08-01","Message Proofs Delivered to Client","QA","On-going","PLANNED",null,"2002-09-09","AE"]
[null,null,"RITZ-005","2002-08-01","Client Revisions","QA","On-going","PLANNED","2002-09-10","2002-09-11","AE","MH","KM","MG","TT","RW"]
[null,null,"RITZ-006","2002-08-21","Client Approval","QA","On-going","PLANNED",null,"2002-09-11","AE"]
[null,null,"RITZ-007","2002-08-01","Data Loaded","Data","On-going","PLANNED",null,"2002-09-11","AE","MH","KM","MG","JF","RW"]
[null,null,"RITZ-008","2002-08-01","@Once Function QA","QA","On-going","PLANNED","2002-09-12","2002-09-12","AE","MH","KM","MG","TT","RW"]
[null,null,"RITZ-009","2002-08-01","Message Launch:  riz_XXXX","Launch","On-going","PLANNED",null,"2002-09-13","AE","MH","KM","MG","JF","RW"]
[{"$nulls":15}," "]
[null,null,"Please Note:"]
[null,null,"- All Target Completion Dates are equivalent to the end of the day (EOD) unless otherwise specified."]
[]
[]
[]
[{"$nulls":3}," "]